## Slide 1
Comparing LLMs and Fine-Tuned Transformer-Based Models
for Biomedical NER and Relation Extraction
for Knowledge Graph Construction
Mridul Milan
Student No: 25234387
Supervisor: Prof. Peter Paul Buitelaar

## Slide 2
2
Progress Since the Last Meeting
Previous Position
• PubMedBERT NER fine-tuning completed [2].
• Final BioRED test F1-score: 86.54% [1].
• NER evaluation and error analysis completed.
• Next planned stage: PubMedBERT relation extraction.
Progress Since Then
• Completed relation-classification data.
• Generated No_Relation examples.
• Identified marker loss after truncation.
• Started a separate LLM extraction notebook.
Current Status
• NER pipeline complete
• RE data complete
• RE training paused for validation
• LLM pipeline prepared up to model selection
Focus of This Meeting
• Recent implementation progress
• Relation extraction challenge
• LLM pipeline setup
• Supervisor feedback questions
Current Challenge
• Preserving both relation entities inside PubMedBERT’s 512-token input limit

## Slide 3
3
Stage 3.2: Relation Data Completion
Balanced relation-classification dataset completed using BioRED gold relations and generated No_Relation examples [1]
Completed Dataset
• Positive examples from BioRED gold relations [1]
• Equal number of No_Relation examples added
• Entity markers inserted around both arguments
• 8 BioRED relation labels + No_Relation [1]
Final examples
• Train: 8,356
• Development: 2,324
• Test: 2,326
Outputs Saved
• Prepared train/dev/test RE datasets
• Relation label-to-ID mappings
• Entity-marked model inputs
• Files saved to Google Drive
Why this matters
• Provides balanced supervision
• Supports fair relation-classification evaluation
• Prevents training before input validation
Positive + No_Relation examples are now ready for supervised PubMedBERT relation classification
Next validation step: confirm both entity markers survive tokenisation and truncation

## Slide 4
4
Stage 3.3: Relation Validation Challenge
• Validation identified 16 training examples with missing entity markers after tokenisation/truncation [2,3].
• The affected examples had a final sequence length of 512 tokens.
• The issue appears when relation arguments are far apart in long title-and-abstract text.
• Standard truncation may retain one marked entity while removing the other.
• PubMedBERT relation training was paused before using potentially corrupted examples [2].
Issue | Value
Affected split | Training
Examples | 16
Length | 512 tokens
Why this matters
• Relation classification needs both arguments
• Missing markers change the task
• Incorrect inputs could corrupt supervision
Decision
• Pause RE training
• Treat as input-design challenge
• Redesign context strategy before fine-tuning

## Slide 5
5
Current RE Challenge: Preserving Relation Context
• PubMedBERT supports a maximum sequence length of 512 tokens [2,3].
• Some BioRED documents contain relation entities that are far apart.
• Full-document truncation is not always safe for relation classification.
• The model must receive both marked entities and enough surrounding context.
• The challenge is to redesign the input while keeping evaluation fair and reproducible.
Possible Strategy
Long document with distant entities
Locate both relation arguments
Build entity-centred context window
Validate both markers before training
Option | Decision Needed
Repair | Keep examples using safer windows
Exclude | Remove 16 affected examples
Redesign | Use entity-centred truncation

## Slide 6
6
Stage 4: LLM Pipeline Setup
• Created a separate Colab notebook for LLM-based biomedical extraction.
• Defined the 6 BioRED entity categories and 8 relation categories [1].
• Designed strict JSON output containing entities and relations.
• LLM predicts entity text and type; Python recovers exact offsets.
• Added handling for missing mentions and repeated entity mentions.
• This pipeline uses the same BioRED text and schema as the PubMedBERT experiments [1,2].
Split | Docs | Entities | Relations
Train | 400 | 13,351 | 4,178
Dev | 100 | 3,533 | 1,162
Test | 100 | 3,535 | 1,163
Schema Design
• Six entity types
• Eight relation types
• Strict JSON format
• No unsupported labels
• No free-text explanation
Data Prepared
• All 600 documents loaded
• Title + abstract reconstructed
• BioRED offsets preserved
• Gold labels retained for evaluation

## Slide 7
7
Stage 4: Prompt Pipeline and Model Selection
Prompt Validation
• Three development documents selected
• Zero-shot BioRED extraction prompt built
• Required JSON structure checked automatically
• All three pilot prompts passed validation
Selected Model
• Qwen2.5-7B-Instruct
• Open-source instruction model
• Planned in Google Colab
• 4-bit quantisation to reduce GPU memory [5]
API Decision
• OpenAI API could be stronger but costly at full-dataset scale [6]
• 600 documents may increase total cost
• Open-source model improves reproducibility
• No paid API required for main run
• Stage 4 currently ends at model selection and configuration.
• The LLM has not yet been loaded.
• No LLM predictions or evaluation results have been produced yet.
• Next step is controlled inference on the three pilot development documents.
Key status: LLM pipeline is prepared for pilot inference, but extraction has not yet been run

## Slide 8
8
Current Status and Immediate Next Steps
Completed
• PubMedBERT NER evaluation completed: 86.54% F1.
• Relation data completed with balanced No_Relation examples.
• Relation-input validation identified 16 marker-loss cases.
• LLM schema, JSON format, data loading and prompt validation completed.
• Qwen2.5-7B-Instruct selected for open-source LLM testing [4].
Pipeline | Current stage
PubMedBERT NER | Complete
PubMedBERT RE | Paused at validation
LLM extraction | Ready for pilot inference
Immediate Next Steps
• Load Qwen2.5-7B-Instruct in 4-bit mode [4,5]
• Run the three-document pilot
• Parse and validate JSON
• Recover entity offsets
Final Next Steps
• Analyse hallucinations and missed entities
• Freeze prompt after dev testing
• Run final LLM evaluation
• Compare with PubMedBERT
• Store outputs in Neo4j [7]

## Slide 9
9
Current Decisions Requiring Supervisor Feedback
Main Questions
Is Qwen2.5-7B-Instruct an appropriate main LLM for this study [4]?
Should I include an OpenAI model despite API cost across 600 documents [6]?
What is the most suitable way to preserve both marked entities within PubMedBERT’s 512-token limit?
For the 16 affected relation examples, should I repair the inputs using entity-centred context windows or exclude them?
LLM Selection
• Qwen2.5-7B-Instruct vs biomedical LLM
• One model vs small model comparison
• Open-source reproducibility vs paid API benchmark
Relation Extraction Challenge
• Best method to preserve both marked entities
• Repair, exclude, or redesign the 16 cases
• Consider entity-centred context windows
Evaluation Design
• Strict vs relaxed entity matching
• Handling repeated mentions and offsets
• Measuring hallucinations, invalid labels and consistency

## Slide 10
10
References
[1] Y. Luo et al., “BioRED: A Rich Biomedical Relation Extraction Dataset,” Briefings in Bioinformatics, 2022.
[2] Y. Gu et al., “Domain-Specific Language Model Pretraining for Biomedical Natural Language Processing,” ACM Transactions on Computing for Healthcare, 2021.
[3] J. Devlin et al., “BERT: Pre-training of Deep Bidirectional Transformers for Language Understanding,” NAACL-HLT, 2019.
[4] Qwen Team, “Qwen2.5 Technical Report,” arXiv:2412.15115, 2025.
[5] Hugging Face, “Transformers: bitsandbytes Quantization Documentation,” accessed 2026.
[6] OpenAI, “API Pricing,” accessed July 2026.
[7] Neo4j, “Neo4j Graph Database Documentation,” accessed 2026.